## Project Planner
Sprint 3 - Agility
Select a period to highlight at right. A legend describing the charting follows. | [5 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | STAFF MEMBER(S) | PLAN START (Hours) | PLAN DURATION (Hours) | ACTUAL START (Hours) | ACTUAL DURATION (Hours) | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Develop a plan (Gantt chart) | Tennessee | 1 | 1 | 1 | 1 | 100%
Build requirements table | Tennessee | 1 | 1 | 1 | 1 | 100%
Algorithm | Tennesse | 1 | 1 | 1 | 1 | 100%
Flowchart | Tennessee | 1 | 1 | 1 | 1 | 100%
Code Program | Alexander | 2 | 1 | 2 | 1 | 100%
Assigning roles | Tennessee | 2 | 1 | 2 | 1 | 100%
Group requirement table | Tennessee | 2 | 1 | 2 | 1 | 100%
Testing/Gathering Data | Tennessee/Alexander | 3 | 3 | 3 | 2 | 100%
Collect Sensor Data | Alexander | 6 | 1 | 5 | 1 | 100%
Take Video | Wilmary | 6 | 1 | 5 | 1 | 100%
Complete SDD | Tennesse | 7 | 3 | 7 | 3 | 100%
Final Meeting for Uploading Project details | Tennessee | 8 | 1 | 8 | 2 | 100%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%